## SDP-Service
Annex-1
ANNUAL PROCUREMENT PLAN - Procurement of Goods & Services (FY 2021-2022)
Ministry / Division: |  |  | Information and Communication Technology Division | [5 empty] | 128 |  |  |  | Project Cost (In lakh Taka)
Agency: |  |  | Bangladesh Computer Council | [5 empty] | 12801 |  |  |  |  | Total | 4475.02
Procuring Entity Name & Code: |  |  | Project Director | [10 empty] | GoB | 617.34
Project / Programme Name & Code: |  |  | The Project for Skills Development of IT Engineers Targeting Japanese Market | [5 empty] | 2230332 |  |  |  |  | PA | 3857.68
Project Implementation Periods: |  |  | August 2017 -January 2022
Package No | Description of Procument Package SERVICES | Unit | Quantity | Procure-ment Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost (in Lakh Taka) | Time Code for Process | Not Rsed in GOODS | Invite/ Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total Time to Contract Signature | Time for Completion of Contract
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
SD1 | ITEE Training for University's Students | Qty | 1 | DP | PD | GoB | 32 | Planned Dates | - | 2021-08-01 | 2021-08-14 | 2021-08-21 | 2021-08-24 | 2021-08-25 | 2021-08-26 |  | 2021-10-25
[8 empty] | Planned Days | - |  | 10 | 7 | 3 | 1 | 1 | 60 | 60
[8 empty] | Actual Date | -
SD2 | Question Formulation Meeting outside Dhaka | Qty | 1 | DP | PD | GoB | 9 | Planned Dates | - | 2021-12-01 | 2021-12-14 | 2021-12-21 | 2021-12-24 | 2021-12-25 | 2021-12-26 |  | 2022-01-10
[8 empty] | Planned Days | - |  | 10 | 7 | 3 | 1 | 1 | 2 | 15
Actual Date
SD3 | B-JET Booklet | Qty | 1 | RFQ | PD | GoB | 2.5 | Planned Dates |  | 2021-10-01 | 2021-10-14 | 2021-10-21 | 2021-10-24 | 2021-10-25 | 2021-10-26 |  | 2021-11-10
[8 empty] | Planned Days |  |  | 10 | 7 | 3 | 1 | 1 | 15 | 15
Actual Date
Total | 8: 43.5; 9: Lac